PRODUCT REQUIREMENTS DOCUMENT

Expanding into Premium Leather Goods · Printify Supply Pillar

| Owner | Supply PM · Supplier Management | Target | Q1 2026 | Status | Draft | Market | USA · 2025 |
| --- | --- | --- | --- | --- | --- | --- | --- |

01  PROBLEM STATEMENT & MARKET OPPORTUNITY

Problem Statement

Current state: Decorators purchase premium leather blanks but have no Printify channel to list them — they route to Printful or independent channels. Merchants selling personalized gifts and corporate accessories cannot fulfill leather orders through Printify.

Root cause: No leather blueprint schema · No mockup engine support for leather texture · No decoration method config for laser engraving or debossing.

Desired state: Decorators self-onboard leather SKUs in <24h · Merchants list custom leather goods on Etsy, Amazon, Shopify via Printify · AOV premium captured: leather $35–80 vs apparel $18–25.

Market Opportunity (USA 2025)

| Channel | Signal / Search Term | Avg Price | Signal | Source (real data) |
| --- | --- | --- | --- | --- |
| Etsy USA | "custom leather wallet" | $35–70 | HIGH | eRank 2025 — #215 top keyword, 125%+ CTR |
| Etsy USA | "personalized leather bag" | $55–120 | HIGH | ShelfTrend 2025 — $130K–270K weekly GMV |
| Etsy USA | "engraved leather keychain" | $15–35 | HIGH | eRank 2025 — Nov-Dec +57% search growth |
| Amazon USA | "custom leather wallet" | $30–65 | HIGH | accio.com — top SKU 8,365 units/month |
| Amazon USA | "personalized leather gifts" | $22–65 | HIGH | AmzChart — 1.5–3.5× AOV vs apparel |
| TikTok Shop | "laser engraved leather" | $25–45 | HIGH | TikTok Shop category page — 60–80% GM |

| USA leather goods market | $54B (2024) | Leather wallet CAGR | 9.5% (2023–2030) |
| --- | --- | --- | --- |
| Custom/personalized TAM | $2–3B [EST] | POD-compatible segment | $600M–1.2B [EST] |
| AOV premium vs apparel | 1.5–3.5× | Consumers pay engraving premium | 42% (AmzChart) |
| Personalized gifts market USA | $9.7B, +7% CAGR | First-mover window | ~18 months [EST] |

Competitive gap: Gelato: 0 leather products · Printful: PU/faux-leather patches only — no genuine leather (verified Aug 2025). No major POD platform offers genuine leather + personalization at scale.

02  OBJECTIVES & SUCCESS METRICS

| Metric | Baseline | Target (12m post-launch) | Measurement |
| --- | --- | --- | --- |
| Decorator leather time-to-live | N/A | <24 hours | Pipeline timestamp delta |
| Active leather Decorators | 0 | 10 | Printify dashboard |
| Leather SKUs live in catalog | 0 | 1,500 | Catalog tag filter |
| Monthly GMV (platform margin) | $0 | $375K | GMV dashboard — leather tag |
| Decorator auto-approval rate | N/A | >70% | Ingestion layer logs |
| Merchant NPS — leather category | N/A | >7 | Post-launch survey |

03  RECOMMENDED LAUNCH OPTION — LEAN MVP  (scored 15/20)

| Option | Impact | Fit | Effort | Risk | Total | Verdict |
| --- | --- | --- | --- | --- | --- | --- |
| 1 — POC First ($5K · 3w) | 2 | 2 | 1 | 1 | 14 | Not standalone |
| 2 — Lean MVP ($47K · 12–14w) | 4 | 4 | 3 | 2 | 15 | ✓ Recommended |
| 3 — Full Build ($80–100K · 16–20w) | 5 | 5 | 5 | 4 | 13 | Premature |

MVP P0 Features (12–14 weeks):

| ID | Feature | Owner | Duration | Priority |
| --- | --- | --- | --- | --- |
| C1 | Leather blueprint schema | Backend (2 eng) | 3w | P0 |
| C2 | Decoration method config: laser engraving + debossing | Backend (2 eng) | 3w | P0 |
| M1 | Marketplace mapping: Etsy · Amazon · Shopify | Backend (1 eng) | 2w | P0 |
| D1 | Decorator portal: leather SKU submission + error report | Frontend (1 eng) | 2w | P0 |
| F3 | Static mockup — leather texture (dynamic in v2) | Mockup (1 eng) | 4w | P0 |
| C4 | MAT-001: auto-reject Tier 2/3 labeled as Genuine Leather | Backend (1 eng) | 1w | P0 |

Kill criteria: Stop if <3 Decorators live by Week 6 · OR · time-to-live consistently >48h after portal launch · OR · merchant NPS <5 at 90 days.

04  ROI MODEL

| Input | Value | Output | Value |
| --- | --- | --- | --- |
| Active Decorators (steady state) | 10 | Monthly platform margin | $375,000 |
| Avg SKUs per Decorator | 150 | Annual platform margin | $4,500,000 |
| Avg orders / SKU / month | 50 | Total engineering cost | $138,000 |
| Platform margin per order | $5 | Ops cost (12w) | $6,000 |
| Eng. cost / person / week | $3,000 | GTM cost | $5,000 |
| Backend: 3w × 2 eng | $18,000 | Total investment | ~$203,600 |
| Mockup: 4w × 1 eng | $12,000 | Payback from kickoff | ~7 months |
| Frontend: 2w × 1 eng | $6,000 | ⚠️ Critical assumption | 50 orders/SKU/month |

⚠️ Model breaks at 10 orders/SKU/month: payback extends past 30 months. Validate with 2-Decorator pilot before full engineering commitment.

05  RISK ASSESSMENT & DECISION REQUESTED

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Mockup quality insufficient for leather | Medium | High | Pilot 2 Decorators pre-launch · gate on NPS >7 |
| Decorator data quality issues | High | Medium | Per-SKU error codes · self-correct portal · MAT-001 auto-reject |
| Low merchant adoption first 90 days | Medium | Medium | Co-marketing with 3 anchor merchants pre-launch |
| Mockup engine timeline slip | High | High | Decouple: static mockups v1 · dynamic renders v2 |

RECOMMENDATION: GO WITH CONDITIONS

Decision requested: Approve Q1 2026 roadmap inclusion for the Lean MVP — 2 backend engineers + 1 mockup engineer + 1 frontend engineer, starting January 2026 (12–14 weeks). Gate at Week 6: ≥3 Decorators live and time-to-live <24h before continuing to full team rollout.